## Sheet1
Laboratory Prioritization Meeting Decisions and Actions
| Topic | Decision Made | How should the decision be implemented | Issues | Date
1 | Implement Detection Limits | Detection limits should be implemented and those values that are measured and below the detection limits should be set to Zero | The detection limits should be implemented between LIMS and the Repository | There are some negative values in the repository already
2 | Change units of Total P to mg/kg | Adopted mg/kg is the preferred units for data distribution. | The units for P exported from the repository will be mg/kg | There is some older data that is in % P205. That data is being discussed and may be converted to mg P/kg soil | 2014-11-17
3 | Links will be made from the metadata tables to the documentation | This is being started on. Links are being made from the analyte_procedure table to SSIR 42 version 5 | Recommendations have been made to extend this to LIMS, the Repository and the Microsoft ACCESS database | We need to decide how to link to the univerisity methods. | Reaffirmed Nov 21, 2014
4 | Most of the time there should be a single pedon Natural Key for a given pedon description | Cases where there were two Natural Keys for a single pedon are being corrected. This is primarily a RaCA issue | This is a lesson learned from RaCA. In the future sample numbers will be unique for a given pedon sampled on a given date.
5 | Completeness Index | It was decided to deliver both a numeric Completeness Index as well as an alph code which would help identify which data is available for a given pedon | PROCBEW | It did not see feasible to include Rock Fragments at this time. See Oct 7 notes for comlete decision.
6 | University Laboratory Methods | The source system table is used to separate sources of laboratory data | The source system table is maintained in the Lab Data Mart and the source is displayed on the data sheet on the website. | the Microsoft Access database does not currently have a way to distinguish source. Also there are some samples that were analyzed by both a university and by KSSL. Sometimes for the same analysis and sometimes for different analysis or complimentary analysis.
7 | Rock Fragments need attention | So far Cathy Seybold has made some validations in NASIS. There is a long way to go in this one | Rock fragment data of varying completeness is stored in three separate databases. (LIMS, Repo, and NASIS) | Need to find a way to maintain the data that is measured and at the same time integrate the volume estimates to get a more clear picture of the Whole Soil.
8 | Some attributes have been added to the NCSS Lab Layer table in NASIS. Are there others that should be added? | Gypsum on a < 2 mm base needs to be added. Others are being discussed | Gypsum < 2 mm was added to the NASIS 7.1 data model in Sept of 2014.
9 | Flag the default bulk density of 1.45 in the Supplemental Data Tier | It was decided to Flag the Bulk density of 1.45 in the Supplemental Data Tier by comparing the 33 kPa in the supplemental to the primary characterization report (measured bulk density). If there is no measured value, the value of 1.45 is a dafault value and needs a flag. | A superscript after the number in the field, and a note at the bottom of the Supplementary Characterization Data sheet.
10 | A default bulk density of 1.45 is on about 1300 organic horizons. | The default bulk density should be removed from the organic horizons (Oi, Oe, Oa) | Henry will make a spreadsheet of the values and send them to Rich, Steve and Ellis for concurrence.
11 | Need better documentation for use of default values (in the reports) | Three footnotes will be added to the Supplementary Characterization tier. | Rick will add the code to the public website to display the 3 footnotes that have been English edited and agreed upon at the Feb 24 Meeting
12 | Estimates for Bulk Density in the repository with no documentation. | Those values that have corresponding measured values will be deleted. | Rick will delete the esitmates for samples that have real measured values as well.
13 | Some of the Saturated Bulk Densities for the < 2mm fraction are also default values. | A footnote will be added to identify those saturated bulk densities that are default values. | Rick will update the website to add the footnotes to the appropriate values
14 | There is no way to tell which whole soil bulk densities were calculated from measured values, default values, or estimates. | A field will be added to the ACCESS database to identify which whole soil bulk densities were calculated from measured values, default values, or estimated values. | Rick will add the field to the view and include the appropriate logic.
15 | LIMS only has degrees minutes and seconds. Apparently the conversion to decimal degrees In the repository may not reflect WGS84. However, the same sites are in NASIS so they have been converted there. | Decimal degrees fields will be added to LIMS and they will be defined as WGS84 | Add Decimal Degrees WGS84 to LIMS
16 | Make changes to the KSSL laboratory submission sheet and route |  | Route changes to the KSSL submission sheet
| Possibly add 4 fields to the phorizon sample table | Fields for number of bulk samples clods and fabric clods | Possibly add 4 fields to the phsample table
| Make the project folders accessible | It was decided that they should be made available. It is doubtful if there is PII in the folders. People are more careful about that these days | Possiply place the contents of the project folder in a content management system and link to it via a link in the project table. | There is no content management system yet
| Update the Analyte Procedure table | Update the table in Repo, Update the table in the Microsoft ACCESS database | The spreadsheet needs to be maintained somewhere so it does not get lost. Most of the columns will go into Repo and the Microsoft Access database | There are still many rows that have not been identified. Many are associated with the University data
| Syncronize the Area Tables in LIMS Repo and NASIS |  |  | George and Rick will determine what standard has been used. If they can not figure it out a standard will be selected.
| Clean up the Layer Fraction Table |  |  | Rick added the documentation and Rick and Henry will delete rows that do not meet the definition.